## Status Summary
Executive Project Status Summary | Use this sheet to prepare a weekly leadership readout.
Project / Initiative
Reporting Period
Sponsor
Delivery Lead
Overall Status | Green / Yellow / Red
Primary Message
Key Progress
Top Risk
Decision Needed
Next Milestone
Milestone Date
Support Needed
Owner
Notes
How to use | Update this sheet first, then roll detail into the logs on the next tabs.
Clarpoint | Clear plans. Stronger communication. Better execution.

## RAID Log
ID | Type | Description | Impact | Owner | Mitigation / Next Step | Target Date | Status
R-01 | Risk | Approval timing may affect the next milestone | Medium | Program Manager | Confirm owner and decision date | 2026-06-02 | Open
I-01 | Issue | Vendor date is still unconfirmed | High | Delivery Lead | Escalate in weekly readout | 2026-05-30 | In Progress

## Action Tracker
Action ID | Action | Owner | Due Date | Status | Priority | Notes
ACT-01 | Confirm milestone owners | Program Manager | 2026-05-29 | In Progress | High | Review in Monday note
ACT-02 | Draft leadership decision request | Delivery Lead | 2026-05-31 | Open | High | Needs sponsor framing

## Decision Log
Decision ID | Decision | Date | Owner | Reason | Impact | Follow-Up
DEC-01 | Keep phased launch approach | 2026-05-24 | Executive Sponsor | Reduces immediate delivery risk | Scope / timeline | Update milestone plan
DEC-02 | Escalate content dependency | 2026-05-24 | Program Manager | Content timing threatens launch date | Stakeholder communication | Raise in leadership note

## Milestones
Milestone | Owner | Target Date | Current Status | Risk Level | Notes
Requirements sign-off | Business Lead | 2026-06-03 | On Track | Low
Build complete | Tech Lead | 2026-06-18 | At Risk | Medium | Waiting on approvals